## Sheet1
墨迹项目
12 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 时间（h） | 备注
1 | 1 | 1 | user story | 临时记录 | 作为一个偶尔做记录的人，需要临时记录 | Initial Feature | Not Done | 2 | 98 |  | 2
2 | 1 | 1 | user story | 复习式记录 | 作为学习爱好者，可以将本记录APP作为知识整理集 | Initial Feature | Not Done | 1 | 96 |  | 1
3 | 1 | 1 | user story | 账本 | 作为经常花钱的学生，需要流水账来管理费用 | Initial Feature | Not Done | 3 | 95 |  | 3
4 | 1 | 1 | user story | 杂志化记录 | 作为简约美的爱好者，希望用卡片形式记录每次事件 | Initial Feature | Not Done | 1 | 93 |  | 1
5 | 1 | 1 | user story | 管理记录 | 作为随笔爱好者，需要经常记录整理 | Initial Feature | Not Done | 1 | 93 |  | 2
6 | 1 | 1 | user story | 分享交友 | 作为社交爱好者，希望优雅的标签记录，分享给其他人 | Initial Feature | Not Done | 0.5 | 90 |  | 1
8.5
10 | 2 | 2 | user story | 记录整理 | 作为一个记录爱好者，需要按照时间排序或地点分类 | Initial Feature | Not Done | 2 | 23 |  | 2
11 | 2 | 2 | user story | 修改操作 | 作为随笔记录爱好者，需要简单优雅的手势操作，符合人体交互美学 | Initial Feature | Not Done | 1 | 20 |  | 1
12 | 2 | 2 | user story | 事件搜索 | 作为一个记录爱好者，当记录繁多时，需要及时搜索出相应记录 | Initial Feature | Not Done | 1 | 20 |  | 1
4
1 | 3 | 3 | user story | 记录自定义 | 作为一个记录爱好者，在基本功能实现后，希望能自定义各种标签 | Initial Feature | Not Done | 3 | 10 |  | 3
2 | 3 | 3 | user story | 欣赏他人记录 | 作为一个分享记录爱好者，欣赏他人记录也是一种享受 | Initial Feature | Not Done | 20 | 10 |  | 20
Total |  | 11 | [5 empty] | 48
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on C19: Luc Segers: Total amount of stories available in the project backlog
Note on I19: Luc Segers: total amount of estimated hours